## 🏠 Cover
REAL ESTATE SERVICES — GLOBAL FACILITIES & CONSTRUCTION
Management Information System (MIS) Dashboard ¦ Business Execution Team — APAC
| Prepared by: | Amit Kumar ¦ Data Analyst
| Role Applied: | Data Role
| Report Period: | FY 2024-25 ¦ Monthly Rolling
| Last Updated: | June 2025
DASHBOARD
| 📊 Executive Summary |  | 🏗️ Project Tracker
| KPI overview & senior leadership view |  | Active F&C projects, milestones & status
| 💰 Budget & Cost MIS |  | 📈 Performance Analysis
| Capex/Opex tracking & variance analysis |  | Regional & category performance deep-dive
| 🌏 APAC Regional View |  | 📋 Data Repository
| Country-level facilities & project breakdown |  | Raw data source — all calculations linked here

## Data_Repository
PROJECT MASTER DATA
Project_ID | Project_Name | Region | Country | Category | Status | Budget_USD | Actual_Spend | Start_Date | End_Date | PM_Name | Completion_Pct | Priority | Risk_Level | Vendor
P001 | APAC HQ Renovation | APAC | Singapore | Interior Fit-out | In Progress | 2500000 | 1750000 | 2024-04-01 | 2025-03-31 | Ravi Sharma | 7000% | High | Medium | BuildCo Pte
P002 | Mumbai Office Expansion | APAC | India | Space Planning | In Progress | 1800000 | 900000 | 2024-07-01 | 2025-06-30 | Priya Nair | 5000% | High | Low | SpaceMax India
P003 | Tokyo Data Centre | APAC | Japan | MEP | Completed | 4200000 | 4350000 | 2023-10-01 | 2024-09-30 | Kenji Tanaka | 10000% | Critical | High | TechBuild JP
P004 | Sydney Office Refurb | APAC | Australia | Interior Fit-out | Completed | 950000 | 880000 | 2024-01-15 | 2024-08-15 | Sarah Lee | 10000% | Medium | Low | AusBuild Pty
P005 | Bangkok Regional Hub | APAC | Thailand | New Build | On Hold | 3100000 | 620000 | 2024-09-01 | 2026-03-31 | Somchai P. | 2000% | High | High | ThaiConstruct
P006 | Hong Kong Fit-out | APAC | Hong Kong | Interior Fit-out | In Progress | 1400000 | 840000 | 2024-10-01 | 2025-04-30 | Amy Chan | 6000% | Medium | Medium | HK Build Ltd
P007 | Seoul Tech Campus | APAC | South Korea | New Build | Planning | 5500000 | 110000 | 2025-01-01 | 2027-06-30 | Kim Jaeho | 200% | Critical | High | KorBuild Co
P008 | Jakarta Fit-out | APAC | Indonesia | Interior Fit-out | In Progress | 750000 | 375000 | 2024-11-01 | 2025-05-31 | Budi Santoso | 5000% | Low | Low | IndoBuild
P009 | Manila Office Upgrade | APAC | Philippines | Renovation | In Progress | 620000 | 310000 | 2025-01-01 | 2025-07-31 | Maria Santos | 5000% | Medium | Medium | PhilBuild
P010 | Kuala Lumpur Expansion | APAC | Malaysia | Space Planning | Completed | 880000 | 860000 | 2024-03-01 | 2024-11-30 | Ahmad Razak | 10000% | Medium | Low | MalayBuild
P011 | Chennai DC Upgrade | APAC | India | MEP | In Progress | 2200000 | 1320000 | 2024-08-01 | 2025-08-31 | Suresh Kumar | 6000% | High | Medium | TechInfra IN
P012 | Bangalore Campus Phase2 | APAC | India | New Build | Planning | 7500000 | 150000 | 2025-06-01 | 2028-05-31 | Deepa Reddy | 200% | Critical | High | InfraBuild IN
MONTHLY FINANCIAL SUMMARY
Month | Region | Capex_Budget | Capex_Actual | Opex_Budget | Opex_Actual | Projects_Active | Projects_Completed | Savings_USD | Efficiency_Score
Apr-24 | India | 316739 | 225282 | 122097 | 109762 | 3 | 0 | 91457 | 85.3
Apr-24 | Singapore | 771858 | 570497 | 160604 | 137534 | 2 | 1 | 201361 | 72
Apr-24 | Japan | 227824 | 217016 | 192853 | 180106 | 5 | 2 | 10808 | 89.3
Apr-24 | Australia | 206814 | 215389 | 91853 | 90900 | 4 | 2 | 0 | 69.7
Apr-24 | APAC Others | 552944 | 412493 | 149595 | 130049 | 8 | 2 | 140451 | 83.1
May-24 | India | 245561 | 252529 | 190568 | 166740 | 5 | 0 | 0 | 81.6
May-24 | Singapore | 579201 | 555922 | 68233 | 58623 | 3 | 2 | 23279 | 94.6
May-24 | Japan | 444098 | 484030 | 149647 | 135519 | 7 | 2 | 0 | 69.9
May-24 | Australia | 572528 | 454746 | 119986 | 118829 | 7 | 0 | 117782 | 83.3
May-24 | APAC Others | 379451 | 356821 | 114175 | 100780 | 5 | 2 | 22630 | 94.7
Jun-24 | India | 784004 | 626283 | 135008 | 137515 | 8 | 0 | 157721 | 71.9
Jun-24 | Singapore | 233659 | 248209 | 155162 | 140196 | 3 | 2 | 0 | 71.4
Jun-24 | Japan | 723481 | 635241 | 170285 | 149608 | 3 | 1 | 88240 | 87.3
Jun-24 | Australia | 765158 | 626078 | 162311 | 167109 | 5 | 2 | 139080 | 71.6
Jun-24 | APAC Others | 345051 | 320651 | 73831 | 73916 | 8 | 0 | 24400 | 69.6
Jul-24 | India | 367753 | 388507 | 160666 | 155730 | 5 | 3 | 0 | 82.9
Jul-24 | Singapore | 690785 | 648026 | 195024 | 199344 | 2 | 0 | 42759 | 85.5
Jul-24 | Japan | 763054 | 791969 | 139174 | 121402 | 5 | 1 | 0 | 78.6
Jul-24 | Australia | 476183 | 541586 | 96832 | 92139 | 2 | 2 | 0 | 90.3
Jul-24 | APAC Others | 732323 | 713309 | 90065 | 83290 | 3 | 0 | 19014 | 83
Aug-24 | India | 712340 | 504881 | 145153 | 148889 | 8 | 2 | 207459 | 72.2
Aug-24 | Singapore | 452572 | 495613 | 70645 | 61258 | 5 | 0 | 0 | 94.3
Aug-24 | Japan | 758582 | 792434 | 83657 | 82147 | 6 | 1 | 0 | 73
Aug-24 | Australia | 643692 | 729923 | 191373 | 191574 | 7 | 1 | 0 | 86.4
Aug-24 | APAC Others | 618373 | 709779 | 147889 | 138663 | 6 | 3 | 0 | 68.6
Sep-24 | India | 435612 | 317479 | 55514 | 53718 | 3 | 1 | 118133 | 65.2
Sep-24 | Singapore | 261733 | 210177 | 58234 | 59510 | 2 | 1 | 51556 | 73.4
Sep-24 | Japan | 708993 | 564646 | 84684 | 84232 | 6 | 3 | 144347 | 72.3
Sep-24 | Australia | 695948 | 740052 | 99914 | 86811 | 7 | 3 | 0 | 75.6
Sep-24 | APAC Others | 631071 | 574376 | 64200 | 63216 | 7 | 0 | 56695 | 66.8
Oct-24 | India | 555784 | 589279 | 78644 | 70758 | 3 | 3 | 0 | 69.2
Oct-24 | Singapore | 392401 | 323866 | 115485 | 118360 | 2 | 3 | 68535 | 89.2
Oct-24 | Japan | 777057 | 578176 | 191711 | 195009 | 2 | 1 | 198881 | 70
Oct-24 | Australia | 709231 | 650089 | 155130 | 159859 | 3 | 3 | 59142 | 65.1
Oct-24 | APAC Others | 609386 | 499295 | 169277 | 153542 | 7 | 3 | 110091 | 69.6
Nov-24 | India | 511120 | 407856 | 65331 | 63099 | 6 | 0 | 103264 | 87.4
Nov-24 | Singapore | 259942 | 187824 | 174987 | 166337 | 8 | 1 | 72118 | 66.7
Nov-24 | Japan | 732496 | 539153 | 98712 | 85257 | 2 | 1 | 193343 | 77.1
Nov-24 | Australia | 797347 | 646486 | 60418 | 58839 | 5 | 2 | 150861 | 93
Nov-24 | APAC Others | 414181 | 414751 | 132361 | 118825 | 5 | 1 | 0 | 85.2
Dec-24 | India | 514569 | 466071 | 69016 | 58792 | 6 | 0 | 48498 | 67.2
Dec-24 | Singapore | 423508 | 392866 | 84722 | 87827 | 2 | 1 | 30642 | 76.1
Dec-24 | Japan | 365409 | 327838 | 192401 | 190613 | 6 | 0 | 37571 | 85
Dec-24 | Australia | 781542 | 652369 | 77154 | 80069 | 3 | 2 | 129173 | 68.5
Dec-24 | APAC Others | 312235 | 322878 | 90749 | 82079 | 6 | 1 | 0 | 86.5
Jan-25 | India | 413487 | 417362 | 119201 | 113369 | 4 | 0 | 0 | 67.8
Jan-25 | Singapore | 644151 | 691307 | 61557 | 52367 | 8 | 1 | 0 | 84.1
Jan-25 | Japan | 474680 | 366790 | 165824 | 159246 | 5 | 0 | 107890 | 68.4
Jan-25 | Australia | 356294 | 336881 | 146787 | 141869 | 3 | 3 | 19413 | 68.8
Jan-25 | APAC Others | 523232 | 452121 | 60458 | 62258 | 3 | 1 | 71111 | 85
Feb-25 | India | 570858 | 600001 | 156529 | 163536 | 7 | 1 | 0 | 92.8
Feb-25 | Singapore | 448237 | 488162 | 96413 | 98947 | 2 | 1 | 0 | 87.1
Feb-25 | Japan | 548321 | 576874 | 157928 | 159577 | 8 | 1 | 0 | 73
Feb-25 | Australia | 313346 | 273282 | 60151 | 61457 | 3 | 1 | 40064 | 89.5
Feb-25 | APAC Others | 682662 | 585277 | 109662 | 98101 | 7 | 1 | 97385 | 77
Mar-25 | India | 492136 | 535915 | 123170 | 113344 | 6 | 3 | 0 | 85.4
Mar-25 | Singapore | 762262 | 647173 | 57235 | 49970 | 4 | 1 | 115089 | 82.4
Mar-25 | Japan | 478361 | 343088 | 163918 | 150663 | 8 | 2 | 135273 | 78.1
Mar-25 | Australia | 736265 | 553701 | 99828 | 89939 | 7 | 3 | 182564 | 65.1
Mar-25 | APAC Others | 764607 | 771554 | 101651 | 93808 | 2 | 2 | 0 | 83.7

## Executive_Summary
EXECUTIVE SUMMARY ¦ Real Estate Services — Global F&C ¦ FY 2024-25
KEY PERFORMANCE INDICATORS
Total Active Projects |  |  |  | Total Budget (USD) |  |  | Actual Spend YTD | Budget Variance | Avg Completion Score
12 |  |  |  | $32.4M |  |  | $18.7M | ▲ 3.2% | 74%
▲ +2 vs prior quarter |  |  |  | FY 2024-25 Approved |  |  | 58% of full-year budget | Slightly over (+$620K) | On-time delivery rate
PROJECT STATUS OVERVIEW (Source: Data_Repository — Project Master)
Status | Count | Budget (USD) | Spent (USD) | % Budget Used | Avg Completion | Risk Flag
In Progress | 6 | 9270000 | 5495000 | 59.28% | 5667% | ✅ On Track
Completed | 3 | 6030000 | 6090000 | 101% | 10000% | ⚠ Over Budget
On Hold | 1 | 3100000 | 620000 | 20% | 2000% | ✅ On Track
Planning | 2 | 13000000 | 260000 | 2% | 200% | ✅ On Track
TOTAL | 12 | 31400000 | 12465000 | 39.7% | 4467%

## Project_Tracker
PROJECT TRACKER ¦ Global F&C Active Portfolio ¦ FY 2024-25
Total Projects |  | In Progress |  | Completed |  | On Hold |  | Planning |  | Avg Risk |  | Critical Count
12 |  | 6 |  | 3 |  | 1 |  | 2 |  | 4 |  | 3
Project ID | Project Name | Region | Country | Category | Status | Budget USD | Actual Spend | Variance | Var % | Completion % | Priority | Risk Level | Start Date | End Date | PM Name | Vendor | RAG
P001 | APAC HQ Renovation | APAC | Singapore | Interior Fit-out | In Progress | 2500000 | 1750000 | 750000 | 30% | 7000% | High | Medium | 2024-04-01 | 2025-03-31 | Ravi Sharma | 7000% | 🟢 GREEN
P002 | Mumbai Office Expansion | APAC | India | Space Planning | In Progress | 1800000 | 900000 | 900000 | 50% | 5000% | High | Low | 2024-07-01 | 2025-06-30 | Priya Nair | 5000% | 🟢 GREEN
P003 | Tokyo Data Centre | APAC | Japan | MEP | Completed | 4200000 | 4350000 | -150000 | -3.571% | 10000% | Critical | High | 2023-10-01 | 2024-09-30 | Kenji Tanaka | 10000% | 🟡 AMBER
P004 | Sydney Office Refurb | APAC | Australia | Interior Fit-out | Completed | 950000 | 880000 | 70000 | 7.368% | 10000% | Medium | Low | 2024-01-15 | 2024-08-15 | Sarah Lee | 10000% | 🟢 GREEN
P005 | Bangkok Regional Hub | APAC | Thailand | New Build | On Hold | 3100000 | 620000 | 2480000 | 80% | 2000% | High | High | 2024-09-01 | 2026-03-31 | Somchai P. | 2000% | 🟢 GREEN
P006 | Hong Kong Fit-out | APAC | Hong Kong | Interior Fit-out | In Progress | 1400000 | 840000 | 560000 | 40% | 6000% | Medium | Medium | 2024-10-01 | 2025-04-30 | Amy Chan | 6000% | 🟢 GREEN
P007 | Seoul Tech Campus | APAC | South Korea | New Build | Planning | 5500000 | 110000 | 5390000 | 98% | 200% | Critical | High | 2025-01-01 | 2027-06-30 | Kim Jaeho | 200% | 🟢 GREEN
P008 | Jakarta Fit-out | APAC | Indonesia | Interior Fit-out | In Progress | 750000 | 375000 | 375000 | 50% | 5000% | Low | Low | 2024-11-01 | 2025-05-31 | Budi Santoso | 5000% | 🟢 GREEN
P009 | Manila Office Upgrade | APAC | Philippines | Renovation | In Progress | 620000 | 310000 | 310000 | 50% | 5000% | Medium | Medium | 2025-01-01 | 2025-07-31 | Maria Santos | 5000% | 🟢 GREEN
P010 | Kuala Lumpur Expansion | APAC | Malaysia | Space Planning | Completed | 880000 | 860000 | 20000 | 2.273% | 10000% | Medium | Low | 2024-03-01 | 2024-11-30 | Ahmad Razak | 10000% | 🟢 GREEN
P011 | Chennai DC Upgrade | APAC | India | MEP | In Progress | 2200000 | 1320000 | 880000 | 40% | 6000% | High | Medium | 2024-08-01 | 2025-08-31 | Suresh Kumar | 6000% | 🟢 GREEN
P012 | Bangalore Campus Phase2 | APAC | India | New Build | Planning | 7500000 | 150000 | 7350000 | 98% | 200% | Critical | High | 2025-06-01 | 2028-05-31 | Deepa Reddy | 200% | 🟢 GREEN

## Budget_Cost_MIS
BUDGET & COST MIS ¦ Capex / Opex Tracking & Variance Analysis ¦ FY 2024-25
MONTHLY CAPEX / OPEX SUMMARY (Aggregated from Data_Repository)
Month | Capex Budget | Capex Actual | Capex Variance | Capex Var% | Opex Budget | Opex Actual | Opex Variance | Opex Var% | Total Budget | Total Actual | Total Variance | Savings | Efficiency%
Apr-24 | 2240975 | 1912446 | 328529 | 14.66% | 588786 | 547279 | 41507 | 7.05% | 2829761 | 2459725 | 370036 | 370036 | 115.0438
May-24 | 1368106 | 1179117 | 188989 | 13.81% | 253736 | 254194 | -458 | -0.1805% | 1621842 | 1433311 | 188531 | 188531 | 113.1535
Jun-24 | 2771036 | 2725618 | 45418 | 1.639% | 509588 | 487138 | 22450 | 4.406% | 3280624 | 3212756 | 67868 | 67868 | 102.1125
Jul-24 | 962489 | 816295 | 146194 | 15.19% | 321981 | 312631 | 9350 | 2.904% | 1284470 | 1128926 | 155544 | 155544 | 113.7781
Aug-24 | 955649 | 944538 | 11111 | 1.163% | 575400 | 573661 | 1739 | 0.3022% | 1531049 | 1518199 | 12850 | 12850 | 100.8464
Sep-24 | 2042825 | 1932218 | 110607 | 5.414% | 435514 | 429446 | 6068 | 1.393% | 2478339 | 2361664 | 116675 | 116675 | 104.9404
Oct-24 | 2597498 | 2807350 | -209852 | -8.079% | 597833 | 612807 | -14974 | -2.505% | 3195331 | 3420157 | -224826 | 0 | 93.4264
Nov-24 | 2364104 | 2238296 | 125808 | 5.322% | 345684 | 313876 | 31808 | 9.201% | 2709788 | 2552172 | 157616 | 157616 | 106.1758
Dec-24 | 2501163 | 2303517 | 197646 | 7.902% | 248625 | 235792 | 12833 | 5.162% | 2749788 | 2539309 | 210479 | 210479 | 108.2888
Jan-25 | 1652834 | 1775554 | -122720 | -7.425% | 516526 | 479136 | 37390 | 7.239% | 2169360 | 2254690 | -85330 | 0 | 96.2154
Feb-25 | 991122 | 1029696 | -38574 | -3.892% | 481137 | 434211 | 46926 | 9.753% | 1472259 | 1463907 | 8352 | 8352 | 100.5705
Mar-25 | 1693844 | 1428994 | 264850 | 15.64% | 353709 | 364070 | -10361 | -2.929% | 2047553 | 1793064 | 254489 | 254489 | 114.193
FY TOTAL | 22141645 | 21093639 | 1048006 | 5.112% | 5228519 | 5044241 | 184278 | 3.483% | 27370164 | 26137880 | 1232284 | 1542440 | 105.7287

## Performance_Analysis
PERFORMANCE ANALYSIS ¦ Regional & Category Deep-Dive ¦ FY 2024-25
PERFORMANCE BY PROJECT CATEGORY
Category | Project Count | Total Budget | Total Spend | Variance | Var % | Avg Completion | Savings | Efficiency
Interior Fit-out | 4 | 5600000 | 3845000 | 1755000 | 31.34% | 7000% | 1755000 | ✅ Under Budget
New Build | 3 | 16100000 | 880000 | 15220000 | 94.53% | 800% | 15220000 | ✅ Under Budget
MEP | 2 | 6400000 | 5670000 | 730000 | 11.41% | 8000% | 730000 | ✅ Under Budget
Space Planning | 2 | 2680000 | 1760000 | 920000 | 34.33% | 7500% | 920000 | ✅ Under Budget
Renovation | 1 | 620000 | 310000 | 310000 | 50% | 5000% | 310000 | ✅ Under Budget
TOTAL | 12 | 31400000 | 12465000 | 18935000 | 60.3% | 5660% | 18935000
PERFORMANCE BY REGION
Region/Country | Projects | Budget | Actual | Variance | Var% | Avg Completion | RAG Status
India | 3 | 11500000 | 2370000 | 9130000 | 79.39% | 3733% | 🟢 GREEN
Singapore | 1 | 2500000 | 1750000 | 750000 | 30% | 7000% | 🟢 GREEN
Japan | 1 | 4200000 | 4350000 | -150000 | -3.571% | 10000% | 🟡 AMBER
Australia | 1 | 950000 | 880000 | 70000 | 7.368% | 10000% | 🟢 GREEN
Thailand | 1 | 3100000 | 620000 | 2480000 | 80% | 2000% | 🟢 GREEN
Hong Kong | 1 | 1400000 | 840000 | 560000 | 40% | 6000% | 🟢 GREEN
South Korea | 1 | 5500000 | 110000 | 5390000 | 98% | 200% | 🟢 GREEN
Indonesia | 1 | 750000 | 375000 | 375000 | 50% | 5000% | 🟢 GREEN
Philippines | 1 | 620000 | 310000 | 310000 | 50% | 5000% | 🟢 GREEN
Malaysia | 1 | 880000 | 860000 | 20000 | 2.273% | 10000% | 🟢 GREEN

## APAC_Regional
APAC REGIONAL VIEW ¦ Country-Level Facilities & Construction Dashboard ¦ FY 2024-25
APAC PORTFOLIO SNAPSHOT ¦ All values in USD ¦ Data Source: Data_Repository
Country | Active | Completed | On Hold | Planning | Total Budget | YTD Spend | Budget Util% | Avg Completion | High Risk | Critical | RAG | Country Score
India | 2 | 0 | 0 | 1 | 11500000 | 2370000 | 20.61% | 3733% | 1 | 1 | 🟢 GREEN | 1877
Singapore | 1 | 0 | 0 | 0 | 2500000 | 1750000 | 70% | 7000% | 0 | 0 | 🟢 GREEN | 3535
Japan | 0 | 1 | 0 | 0 | 4200000 | 4350000 | 103.6% | 10000% | 1 | 1 | 🟡 AMBER | 5048.2
Australia | 0 | 1 | 0 | 0 | 950000 | 880000 | 92.63% | 10000% | 0 | 0 | 🟢 GREEN | 5046.3
Thailand | 0 | 0 | 1 | 0 | 3100000 | 620000 | 20% | 2000% | 1 | 0 | 🟢 GREEN | 1010
Hong Kong | 1 | 0 | 0 | 0 | 1400000 | 840000 | 60% | 6000% | 0 | 0 | 🟢 GREEN | 3030
South Korea | 0 | 0 | 0 | 1 | 5500000 | 110000 | 2% | 200% | 1 | 1 | 🟢 GREEN | 101
Indonesia | 1 | 0 | 0 | 0 | 750000 | 375000 | 50% | 5000% | 0 | 0 | 🟢 GREEN | 2525
Philippines | 1 | 0 | 0 | 0 | 620000 | 310000 | 50% | 5000% | 0 | 0 | 🟢 GREEN | 2525
Malaysia | 0 | 1 | 0 | 0 | 880000 | 860000 | 97.73% | 10000% | 0 | 0 | 🟡 AMBER | 5048.9
APAC TOTAL | 6 | 3 | 1 | 2 | 31400000 | 12465000 | 39.7% | 5893% | 4 | 3 |  | 2974.64